## Sheet3
| PROJECT NAME |  | Reputation Management System
Start Date | 2014-12-19
End Date | 2015-01-26
Available Calender Days | 38 | Days |  | 2014-12-30 |  | Holidays / Off Days |  | Total Days | Remarks | Not Started
Working Days(Excl. Holidays) | 27 | Days |  |  |  | Weekends |  | 21,27,28,4,10,11,18,24,26,25 |  | In Progres
Team Capacity | 218.7 | Hrs |  |  |  | Govt Holidays |  | 1 |  | Done
Task Estimate | 218.5 | Hrs |  |  |  | Total |  | 11 |  | On Hold
Developer Name | Leaves | Available Days | Working Hours/Day | Working Capacity (Hr) | Total Assigned Task |  | MileStones | Delivery Date | Hours
Sunny | 0 | 27 | 8.1 | 218.7 | 0 |  | Milestone 1 |  | 56
[7 empty] | Milestone 2 |  | 55
[7 empty] | Milestone 3 |  | 54.5
Total |  |  | 8.1 | 218.7 | 0 |  | Milestone 4 |  | 53
Task / Bugs Detail | Hours | Developer | Start Date | End Date | Task URL | Milestones |  | Comments | Completed Status
Agency Level
Login for agency level user along with html integration | 2 |  |  |  |  | Milestone 1
Forgot Password | 2 |  |  |  |  | Milestone 1
DashBoard
Integrate the Dashboard Html | 1 |  |  |  |  | Milestone 1
Feedback Center
List all business created by logged in agency user | 2 |  |  |  |  | Milestone 1
Search: Search will be done on business name only | 1 |  |  |  |  | Milestone 1
Average Rating : Average rating by all users | 4 |  |  |  |  | Milestone 2
Sorting needs to be done on all columns in grid. | 1 |  |  |  |  | Milestone 1
Pagination will be used for grid | 2 |  |  |  |  | Milestone 1
Overall Feedback Rating
Average of Average Rating of all business under logged in user | 3 |  |  |  |  | Milestone 2
List Top three best average rated business | 1 |  |  |  |  | Milestone 2
List Worst Average rated business | 1 |  |  |  |  | Milestone 2
This average will be updated in database at the time when new feedback will be given by customer | 1 |  |  |  |  | Milestone 2
Manage Business User
Html Integration for the Listing Page | 1 |  |  |  |  | Milestone 1
List Business Owner dynamically from the database | 2 |  |  |  |  | Milestone 1
Implement the pagination for the manage business user listing page | 2 |  |  |  |  | Milestone 1
Action Button Functionality
Edit Business user | 2 |  |  |  |  | Milestone 1
Delete Business user | 1 |  |  |  |  | Milestone 1
Manage:- Redirect the user to business dashboard | 1 |  |  |  |  | Milestone 1
Add Business Owner
Html Form Integration | 1 |  |  |  |  | Milestone 1
Applying client Side Validation | 1 |  |  |  |  | Milestone 1
Fetching the list of categories from the database and shown that in dropdown of Add form | 1 |  |  |  |  | Milestone 1
Fetch the list of countries from the database and shown that in dropdown of Add form | 1 |  |  |  |  | Milestone 1
Make ajax call to populate state drop-down based on selected country from the database | 1 |  |  |  |  | Milestone 1
Fetch the list of social sites from the database and populate the social-sharing checker and visibility checker dropdown wiith that,both the dropdown are multi-selected | 1 |  |  |  |  | Milestone 1
Add a multi-select drop-down in form which will populate the Social Media sites | 1 |  |  |  |  | Milestone 1
Capturing the add form info and saving that to the database | 2 |  |  |  |  | Milestone 1
My Site Page
Html Integration along with various color picker | 1 |  |  |  |  | Milestone 1
Applying Client Side Validation | 1 |  |  |  |  | Milestone 1
Saving the form data in db along with File-upload | 2 |  |  |  |  | Milestone 1
Apply the "My Site Page" setting on the agency site | 2 |  |  |  |  | Milestone 1
Reporting
Reporting Page html integration | 1 |  |  |  |  | Milestone 1
Global Filter Dropdown by Business | 2 |  |  |  |  | Milestone 2
Customer Feedback Success- Bar Chart | 3 |  |  |  |  | Milestone 2
Pie Chart | 2 |  |  |  |  | Milestone 2
Star rating Table | 2 |  |  |  |  | Milestone 2
Reviews lisitng with pagination | 2 |  |  |  |  | Milestone 1
Search by First Name, Last Name, Business Name | 2 |  |  |  |  | Milestone 1
Filter By Star ratings | 2 |  |  |  |  | Milestone 2
Apply sorting on all fields | 1 |  |  |  |  | Milestone 1
customer detail page | 1 |  |  |  |  | Milestone 1
Admin
To Add/Edit Admin Account Profile Infomation, My Account Details (Eamil Address,Add Email Address,First Name,Last Name,Company Name, Street Add 1, Street Add2, Country, State.,City,Zip, Phone,Zip,Co Web Address, Sub Domain Name,Domain Name, Agency Logo. (Submit Button) | 4 |  |  |  |  | Milestone 2
Register Email NOtificatoin Section: Business Owner Sign Up Link predefined, Show Biusiness Link (Option), Email Subject, Sender Name,Sender Email, Email Content, Signature, Restore Default Button, Get Meger Fields (Button Submit.) | 4 |  |  |  |  | Milestone 2
Upload Banner: Upload Banner (File upload Control), Current Banner (Banner Image Preview), Landing Page Url on Banner, (Submit Button) | 1 |  |  |  |  | Milestone 2
Email For Talk To Reputation Pro : Email Address (Subnit Button), | 1 |  |  |  |  | Milestone 2
Change Password | 1 |  |  |  |  | Milestone 2
Training
Integrate the training page html along with video by fetching from database | 2 |  |  |  |  | Milestone 1
Visibility
R&d hour provided by client for searching part is 15.We will provide the report of 15 hour's | 15 |  |  |  |  | Milestone 2
Integrate the visiblity page html with the application | 2 |  |  |  |  | Milestone 2
Show the business information by picking from the database | 1 |  |  |  |  | Milestone 2
Calculate the visibility Percentage by fetching the data from the database | 5 |  |  |  |  | Milestone 2
Subscriber -Business User
Login for subscriber level user along with html integration | 2 |  |  |  |  | Milestone 3
Forgot password | 2 |  |  |  |  | Milestone 3
Remember Me | 1 |  |  |  |  | Milestone 3
Register Now html Integration along with fetching country and state from the database | 1 |  |  |  |  | Milestone 3
Adding client side validation | 1 |  |  |  |  | Milestone 3
Send Registration confirmation email along with login credentials | 1 |  |  |  |  | Milestone 3
Saving the info to db | 1 |  |  |  |  | Milestone 3
Dashboard
Welcome text | 0.5 |  |  |  |  | Milestone 3
Get Help | 0.5 |  |  |  |  | Milestone 3
Most recent feedback | 4 |  |  |  |  | Milestone 3
Online Rating Breakdown(From database) | 2 |  |  |  |  | Milestone 3
Most recent online reviews(From database) | 2 |  |  |  |  | Milestone 3
Overall Feedback rating(From database) | 3 |  |  |  |  | Milestone 3
Total reviews(From database) | 2 |  |  |  |  | Milestone 3
Average Online Rating | 2 |  |  |  |  | Milestone 3
Talk to Reputation Pro | 2 |  |  |  |  | Milestone 3
Show Asscoiated agency logo at right bottom | 0.5 |  |  |  |  | Milestone 3
My Visibility | 3 |  |  |  |  | Milestone 3
My Contact Manager
List all the customer of the current business owner and sorting on First Name | 2 |  |  |  |  | Milestone 3
Adding pagination to the list of customers | 2 |  |  |  |  | Milestone 3
Adding the search based on the various filters like 1 star,2 start etc | 4 |  |  |  |  | Milestone 3
Edit and delete the customer info | 2 |  |  |  |  | Milestone 3
Add new Customer info | 4 |  |  |  |  | Milestone 3
Start Initial feedback Sequence | 4 |  |  |  |  | Milestone 3
Send the reaches email out for review along with review page link | 1 |  |  |  |  | Milestone 4
Integrate the html of the page and add client side validation where customer can put the review | 1 |  |  |  |  | Milestone 4
Saving the review in the database | 1 |  |  |  |  | Milestone 4
Send the thank-you email once the customer left the review along with link to share the review on social sharing sites | 1 |  |  |  |  | Milestone 4
Postive FeedbackPage Html Integration ,on this page customer will redirect if the review is postive | 1 |  |  |  |  | Milestone 4
Send the negative feedback email if the review is negative | 1 |  |  |  |  | Milestone 4
Negative FeedbackPage Html Integration along with form,on this page customer will redirect if the review is negative | 1 |  |  |  |  | Milestone 4
Save the cutomer feedback in db and send email to admin | 2 |  |  |  |  | Milestone 4
Bulk import the customers info through csv file | 4 |  |  |  |  | Milestone 4
Export the customer info to csv file by selecting the various filters which business owner can choose by selecting from the pop up | 6 |  |  |  |  | Milestone 4
Implement the quick add customer info functionality in pop up | 3 |  |  |  |  | Milestone 4
My Email Manager
Email Template listing along with the pagination | 4 |  |  |  |  | Milestone 4
Add new Email Template | 4 |  |  |  |  | Milestone 3
Search | 1 |  |  |  |  | Milestone 3
Preview | 1 |  |  |  |  | Milestone 3
Reporting
Show Report on the basis of various parameter like "All Time","Filter By Employee" | 3 |  |  |  |  | Milestone 4
Customer Details View | 1 |  |  |  |  | Milestone 4
Front End Micro Page | [5 empty] | Milestone 4
Integrate the Html | 2 |  |  |  |  | Milestone 4
Show the info of the business dynamically from the database | 1 |  |  |  |  | Milestone 4
Show the google map | 1 |  |  |  |  | Milestone 4
List the client reviews | 2 |  |  |  |  | Milestone 4
show the overall feedback rating | 1 |  |  |  |  | Milestone 4
Show the business office hours from the database | 1 |  |  |  |  | Milestone 4
Database Design | 12 |  |  |  |  | Milestone 1
Testing | 15 |  |  |  |  | Milestone 4
Proof Of Concept
Need to find APi for country and state
Proof of concept for visibility level and find out how to get details from these sites and how we can add particular business to these sites
Read the reviews from the social sites
Not Started
In Progres
Done
On Hold